## Risk Register
RISK REGISTER
ID | Risk Name | Date Raised | Risk & Impact Description | Likelihood | Consequences | Overall | Proposed Mitigation | Owner | Target Date to Resolve | Status
1 | Computer Malfunction | 2021-09-21 | An issue in which my computer is not functional to the point that I cannot work on the project. | Possible | Major | High | Switch to laptop and use github backup. | Reuben |  | open
2 | Loss of Internet Connection | 2021-09-21 | Lack of internet caused by any number of external variables that stops me from accessing online resources and backups. | Unlikely | Minor | Low | Use offline resources to continue working on project. | Reuben |  | open
3 | Backup Failure | 2021-09-21 | Github backups failing for whatever reason. May be cause by the user or the service. | Rare | Minor | Low | Use the local versions of the backed up files and create local backups in case of error. | Reuben |  | open

## Issues Register
ISSUES REGISTER
ID | Date Raised | Project | Issue Title | Issue Description | Specific Deliverable/Milestone affected | Likelihood | Consequences | Overall Issue Rating | Proposed Resolution / Mitigating Action | Issue Owner | Target Date to Resolve | Progress Status / Commentary | Open / Closed

## Risk Matrix
Unitec RISK FRAMEWORK
Likelihood/Impact | Insignificant | Minor | Moderate | Major | Catastrophic
Almost Certain | Moderate | High | High | Extreme | Extreme
Likely | Moderate | Moderate | High | Extreme | Extreme
Possible | Low | Moderate | High | High | Extreme
Unlikely | Low | Low | Moderate | High | High
Rare | Low | Low | Moderate | Moderate | High

## Data (hidden)
Likelihood | Consequences
Almost Certain | Insignificant
Likely | Minor
Possible | Moderate
Unlikely | Major
Rare | Catastrophic